## Sheet1
Phase | Task | Planned start date | Planned end date | Planned duration | Actual start date | Actual end date | Actual duration | The Doer | Notes and Remarks
Preparing for the project | Coursework and reading | 01/06/2026 09:00 AM | 07/06/2026 05:00 PM | 6 days 8 hrs | 09/06/2026 09:00 AM | 14/06/2026 05:00 PM | 5 days 8 hrs | All Team Members | Completed by all
| Set up a team folder on a shared drive | 05/06/2026 10:00 AM | 06/06/2026 06:00 PM | 1 days 8 hrs | 16/06/2026 10:00 AM | 17/06/2026 06:00 PM | 1 day | Leader | Access given to members
Defining the problem | Background reading | 08/06/2026 09:00 AM | 14/06/2026 05:00 PM | 6 days 8 hrs | 18/06/2026 09:00 AM | 24/06/2026 05:00 PM | 6 days 8 hrs | Team Members | Done
| Research issues in our community | 15/06/2026 09:00 AM | 21/06/2026 05:00 PM | 6 days 8 hrs | 23/06/2026 09:00 AM | 28/06/2026 05:00 PM | 5 days 8 hrs | Team Members | Done
| Team meeting to discuss issues and select an issue for the project | 22/06/2026 11:00 AM | 23/06/2026 04:00 PM | 1 days 5 hrs | 05/07/2026 11:00 AM | 05/07/2026 04:00 PM | 5 hrs | Team Members | Done
| Complete section 3 of the Project logbook | 24/06/2026 09:00 AM | 27/06/2026 06:00 PM | 3 days 9 hrs | 01/07/2026 09:00 AM | 03/07/2026 06:00 PM | 5 days | Leader | Completed
Understanding the users | Identify users | 01/07/2026 09:00 AM | 04/07/2026 05:00 PM | 3 days 8 hrs | 08/07/2026 09:00 AM | 11/07/2026 05:00 PM | 3 days 8 hrs | Data Analyst | Found the right users
| Meeting with users to observe them | 05/07/2026 10:00 AM | 10/07/2026 04:00 PM | 5 days 6 hrs | 18/07/2026 10:00 AM | 23/07/2026 04:00 PM | 5 days 6 hrs | Data Analyst & Leader | Collected Info about the work
| Interview with user (1) | 11/07/2026 10:00 AM | 12/07/2026 12:00 PM | 1 days 2 hrs | 25/07/2026 10:00 AM | 27/07/2026 12:00 PM | 2 days 2 hrs | Data Analyst | Found the needs
| Interview with user (2) | 13/07/2026 02:00 PM | 14/07/2026 04:00 PM | 1 days 2 hrs | 20/07/2026 02:00 PM | 21/07/2026 04:00 PM | 1 days 2 hrs | Data Analyst | Found Common issues
| Complete section 4 of the Project logbook | 15/07/2026 09:00 AM | 18/07/2026 06:00 PM | 3 days 9 hrs | 28/07/2026 09:00 AM | 01/08/2026 06:00 PM | 4 days 9 hrs | Leader | Completed
Brainstorming | Team meeting to generate ideas for a solution | 01/09/2026 10:00 AM | 04/09/2026 04:00 PM | 3 days 6 hrs | 11/09/2026 10:00 AM | 15/09/2026 04:00 PM | 4 days 6 hrs | Leader | 2 Members joined
| Complete section 5 of the Project logbook | 05/09/2026 09:00 AM | 07/09/2026 06:00 PM | 2 days 9 hrs | 13/09/2026 09:00 AM | 14/09/2026 06:00 PM | 1 days 9 hrs | Leader | Completed
Designing your solution | Team meeting to design the solution | 09/09/2026 10:00 AM | 13/09/2026 05:00 PM | 4 days 7 hrs | 21/09/2026 10:00 AM | 26/09/2026 05:00 PM | 5 days 7 hrs | All Team Members | Made the Designs
| Complete section 6 of the logbook | 14/09/2026 09:00 AM | 17/09/2026 06:00 PM | 3 days 9 hrs | 25/09/2026 09:00 AM | 27/09/2026 06:00 PM | 2 days 9 hrs | Leader | Completed
Collecting and preparing data | Team meeting to discuss data requirements | 19/09/2026 11:00 AM | 21/09/2026 03:00 PM | 2 days 4 hrs | 02/10/2026 11:00 AM | 03/10/2026 03:00 PM | 1 days 4 hrs | Data Analyst | Discussed on APIs from NASA & ISRO
Collecting and preparing data Prototyping | Data collection | 22/09/2026 09:00 AM | 28/09/2026 06:00 PM | 6 days 9 hrs | 03/10/2026 09:00 AM | 10/10/2026 06:00 PM | 7 days | Data Analyst | Collected APIs
| Data Preparation & Labelling | 29/09/2026 09:00 AM | 04/10/2026 06:00 PM | 5 days 9 hrs | 09/10/2026 09:00 AM | 13/10/2026 06:00 PM | 4 days 9 hrs | Coder | Completed
| Complete Section 6 of the Project logbook | 05/10/2026 09:00 AM | 07/10/2026 06:00 PM | 2 days 9 hrs | 12/10/2026 09:00 AM | 14/10/2026 06:00 PM | 2 days 9 hrs | Leader | Completed
| Team meeting to plan prototyping phase | 08/10/2026 10:00 AM | 09/10/2026 04:00 PM | 1 days 6 hrs | 19/10/2026 10:00 AM | 19/10/2026 04:00 PM | 6 hrs | All Team Members | Completed
Prototyping Testing | Train your model with input dataset | 10/10/2026 09:00 AM | 14/10/2026 06:00 PM | 4 days 9 hrs | 20/10/2026 09:00 AM | 23/10/2026 06:00 PM | 3 days 9 hrs | Coder & Tester | Tested several scores
| Test your model and keep training with more data until you think your model is accurate | 15/10/2026 09:00 AM | 19/10/2026 06:00 PM | 4 days 9 hrs | 28/10/2026 09:00 AM | 02/11/2026 06:00 PM | 5 days 9 hrs | Tester | Reviewed Several Tests and few conclusions
| Write a program to initiate actions based on the result of your model | 20/10/2026 09:00 AM | 23/10/2026 06:00 PM | 3 days 9 hrs | 03/11/2026 09:00 AM | 07/11/2026 06:00 PM | 4 days 9 hrs | Coder | No Sufficient Program was build due to limitations of data
| Complete section 8 of the Project Logbook | 24/10/2026 09:00 AM | 26/10/2026 06:00 PM | 2 days 9 hrs | 02/11/2026 09:00 AM | 05/11/2026 06:00 PM | 3 days 9 hrs | Leader | Completed
| Team meeting to discuss testing time | 28/10/2026 10:00 AM | 28/10/2026 03:00 PM | 5 hrs | 08/11/2026 10:00 AM | 08/11/2026 12:00 PM | 2 hrs | Leader | Completed
Testing Creating the video | Invite users to test your prototype | 29/10/2026 09:00 AM | 29/10/2026 05:00 PM | 8 hrs | 07/11/2026 09:00 AM | 07/11/2026 05:00 PM | 8 hrs | Data Analyst | Invited users and tested on grounds
| Conduct testing with users | 30/10/2026 09:00 AM | 31/10/2026 06:00 PM | 1 days 9 hrs | 08/11/2026 09:00 AM | 11/11/2026 06:00 PM | 3 days 9 hrs | Data Analyst | Several Errors came
| Complete section 9 of the Project Logbook | 31/10/2026 09:00 AM | 31/10/2026 06:00 PM | 9 hrs | 13/11/2026 09:00 AM | 14/11/2026 06:00 PM | 1 days 9 hrs | Leader | Completed
| Team meeting to discuss video creation | 31/10/2026 10:00 AM | 31/10/2026 01:00 PM | 3 hrs | 07/11/2026 10:00 AM | 07/11/2026 01:00 PM | 3 hrs | Leader | Discussion Held at Google Meet
| Write your script | 31/10/2026 02:00 PM | 31/10/2026 06:00 PM | 4 hrs | 07/11/2026 02:00 PM | 08/11/2026 06:00 PM | 1 days 4 hrs | Leader | Completed
| Film your video | 31/10/2026 09:00 AM | 31/10/2026 06:00 PM | 9 hrs | 13/11/2026 09:00 AM | 14/11/2026 06:00 PM | 1 days 9 hrs | Video Editor | Completed
| Edit your video | 31/10/2026 09:00 AM | 31/10/2026 08:00 PM | 11 hrs | 08/11/2026 09:00 AM | 08/11/2026 08:00 PM | 11 hrs | Video Editor | Completed
Completing the logbook | Reflect on the project with your team | 31/10/2026 10:00 AM | 31/10/2026 01:00 PM | 3 hrs | 12/11/2026 10:00 AM | 12/11/2026 01:00 PM | 3 hrs | All Team Members | Reflected and Proposed new ideas
| Complete sections 10 and 11 of the Project Logbook | 31/10/2026 02:00 PM | 31/10/2026 06:00 PM | 4 hrs | 14/11/2026 02:00 PM | 16/11/2026 06:00 PM | 2 days 4 hrs | Leader | Completed
| Review your Project logbook and Video | 31/10/2026 06:00 PM | 31/10/2026 09:00 PM | 3 hrs | 14/11/2026 06:00 PM | 14/11/2026 09:00 PM | 3 hrs | All Team Members | Reviewed all footage and Documents
Submission | Submit your entries on IBM | 31/10/2026 09:00 PM | 31/10/2026 11:59 PM | 2 hrs | 11/11/2026 09:00 PM | 11/11/2026 11:59 PM | 2 hrs | Leader | Submitted